Project Proposal

A proposal under the Education and WASH Program

For

WASH Infrastructure Improvement and Hygiene Awareness for Zebak Secondary School, Badakhshan Province

Project Location: Zebak Secondary School, Zebak District, Badakhshan Province, Afghanistan

Submitted By:

PMIC of Lazuli Pamir Consulting, Afghanistan

Address: Shahr-e-Naw, Kabul, Afghanistan

Phone: 0749055531

Email: pmic@lazulipamir.com

Website: www.lazulipmic.com

Submitted to:

Water Global Practice
South Asia Region (SAR)
World Bank Group
Kabul Country Office
Kabul, Afghanistan

Date of Submission:

07 August 2025

This proposal is submitted as part of the PMIC of Lazuli Pamir Consulting’s commitment to improving WASH infrastructure and hygiene education in underserved schools across Afghanistan, contributing to better health and educational outcomes for children.

Contents

Organization Information:	3

Executive Summary:	3

Problem Statement:	5

Background:	5

Needs Statement:	6

Theory of Change:	7

Logical Framework:	7

Target Beneficiaries:	9

Risk Analysis & Mitigation Plan:	10

Detailed Budget Plan:	11

Work Plan:	13

Monitoring, Evaluation, Accountability & Learning (MEAL) Plan:	16

Sustainability & Exit Strategy:	17

Gender, Protection, and Inclusion Strategy:	19

Implementation and Coordination Arrangements:	20

Annexes / Appendices:	22

# Organization Information:

The PMIC of Lazuli Pamir Consulting (PMIC) is a not-for-profit international development agency established in 1967, and operating in Afghanistan since 2002. As part of the Lazuli Pamir Consulting (PMIC), PMIC-Afghanistan is committed to improving the quality of life of vulnerable communities through long-term, community-driven, and inclusive development. PMIC’s mission in Afghanistan focuses on multi-sectoral programming in education, health, agriculture and food security, economic inclusion, natural resource management, civil society strengthening, and rural development. With a strong emphasis on gender equality, resilience building, and institutional partnerships, PMIC works in remote and conflict-affected regions, prioritizing community participation and sustainability. PMIC-Afghanistan is legally registered with the Ministry of Economy and operates across several provinces including Badakhshan, Bamyan, Baghlan, Samangan, Takhar, and Kabul. It has implemented numerous donor-funded projects supported by the World Bank, EU, USAID, ADB, and various UN agencies. The Foundation maintains a robust financial management system and undergoes regular independent audits to ensure compliance and transparency. With over two decades of experience in Afghanistan, PMIC is widely recognized for its ability to implement complex programs in fragile settings, leveraging its deep-rooted community relationships and cross-sectoral expertise to drive impactful, sustainable change. Project Focal Points – PMIC of Lazuli Pamir Consulting – Afghanistan Name; Position; Responsibility in Project; Contact Information. Eng. Zohra Amiri; Project Manager – WASH Program; Overall project oversight, coordination with stakeholders, and reporting to donor; z.amiri@Lazulipamir.com +93 78 123 4567. Dr. Faridullah Naeem; MEAL Specialist – Education & Health; Monitoring progress, managing data collection, and outcome reporting; f.naeem@Lazulipamir.com +93 79 456 7890. Ms. Laila Habibi; Gender & Inclusion Advisor; Ensuring gender-sensitive design, inclusion, and safeguarding compliance; l.habibi@Lazulipamir.com +93 77 234 5678.

# Executive Summary:

Project Title: WASH Infrastructure Improvement and Hygiene Awareness for Zebak Secondary School, Badakhshan Province, Afghanistan Implementing Agency: PMIC of Lazuli Pamir Consulting – Afghanistan (PMIC-A) Project Duration: 12 months Total Budget: USD 282,650 Project Location: Zebak Secondary School, Zebak District, Badakhshan Province Zebak Secondary School is the only functioning secondary-level institution in one of Afghanistan’s most remote and underserved districts. It currently serves over 1,700 students (55% boys and 45% girls) but suffers from critically inadequate Water, Sanitation, and Hygiene (WASH) facilities. The school lacks access to clean drinking water, has non-functional and unsafe latrines, and no handwashing stations. These gaps contribute to poor student health, frequent illness, high absenteeism—particularly among adolescent girls—and significant barriers to quality education and gender equity. In response, the PMIC of Lazuli Pamir Consulting – Afghanistan (PMIC) proposes a 12-month, integrated WASH intervention aimed at transforming Zebak Secondary School into a healthier, safer, and more inclusive learning environment. The project includes: - Construction of 12 gender-segregated, child-friendly latrines, compliant with SPHERE standards and designed to ensure privacy and menstrual hygiene management (MHM). - Installation of a solar-powered water supply system, handwashing stations, and soap dispensers to promote daily hygiene practices. - Delivery of age-appropriate hygiene education to all 1,700 students, with a strong focus on behavior change and menstrual health awareness. - Distribution of hygiene kits to every student and training for 25 school staff in facility maintenance and hygiene promotion. - Active engagement of the School Management Committee (SMC), teachers, and the District Education Office (DEO) to foster local ownership, accountability, and sustainability. The project’s expected outcomes include: - 100% of students and staff having access to safe and functional WASH facilities; - 80% of students demonstrating improved hygiene behaviors; - A 30% reduction in hygiene-related illnesses and a 20% increase in girls’ school attendance; - Long-term maintenance of facilities by school and government officials post-project. PMIC brings over 20 years of operational experience in Afghanistan, with a proven track record in delivering high-quality WASH, education, and health programs in fragile and remote contexts. As a legally registered NGO with strong community relationships, deep technical expertise, and effective financial and MEAL systems, PMIC is uniquely positioned to deliver this project efficiently, inclusively, and sustainably. This proposal is submitted to the World Bank Group – Water Global Practice, South Asia Region (SAR) as part of PMIC’s broader commitment to improving educational outcomes and gender equity through strengthened WASH infrastructure and awareness in Afghanistan’s most underserved communities.

# Problem Statement:

The proposed intervention targets Zebak Secondary School, located in Zebak District, Badakhshan Province, where over 1,700 students (55% boys and 45% girls) and school staff face severe challenges due to the absence of a functional and inclusive Water, Sanitation, and Hygiene (WASH) system. The core problem is the lack of adequate, gender-sensitive WASH infrastructure and hygiene awareness, which negatively impacts student health, school attendance, and overall well-being. The school lacks clean water, usable toilets, and basic handwashing facilities. This situation particularly affects adolescent girls, who are often forced to miss school due to the lack of privacy and menstrual hygiene facilities. In February 2024, the PMIC of Lazuli Pamir Consulting (PMIC) conducted a WASH Facility Rapid Assessment and Focus Group Discussions (FGDs) with students, teachers, and parents. The assessment revealed that: - 83% of existing latrines were non-functional or unsafe; - 100% of students reported no access to soap or handwashing stations; - 37% of girls aged 12–16 reported missing school days monthly due to poor sanitation; - Teachers cited frequent cases of diarrhea and skin infections among students. Additionally, PMIC’s Key Informant Interviews (KIIs) with school administrators confirmed that WASH-related absenteeism contributes to over 25% of monthly student absences. The root causes include aging infrastructure, lack of investment, weak maintenance systems, and limited hygiene education. Without immediate WASH intervention, the cycle of illness, dropout, and poor academic performance will persist, especially among girls—exacerbating gender inequality and educational exclusion in this remote region.

# Background:

Zebak District, located in the remote mountainous region of Badakhshan Province, is one of Afghanistan’s least developed and most geographically isolated districts. With limited road access, harsh winters, and a scattered rural population, basic services such as education, healthcare, and water supply remain inadequate. Zebak Secondary School is the only functioning secondary school in the district, serving over 1,700 students from surrounding villages, including a growing number of adolescent girls. The target group includes school-aged children (both boys and girls), teachers, and administrative staff who face daily challenges due to the lack of safe and adequate Water, Sanitation, and Hygiene (WASH) facilities. These conditions are especially harmful to girls, who require privacy and dignity to continue their education, particularly during menstruation. The education sector in Zebak faces critical WASH challenges, including: - Non-functional and unsafe latrines - No access to clean drinking water - Lack of hygiene education and poor awareness - No handwashing stations or menstrual hygiene support Although past efforts by local authorities and NGOs have supported minor repairs or health sessions, these have been fragmented and unsustainable due to resource constraints and absence of system-wide investment. Given the deteriorating WASH conditions and increasing student enrollment, the issue has reached a critical point, requiring an integrated and sustainable response. This project comes at a strategic moment to improve health outcomes, safeguard girls' education, and create a safe, inclusive learning environment for all children in Zebak.

# Needs Statement:

The proposed WASH intervention at Zebak Secondary School in Badakhshan Province addresses a critical and urgent gap in basic service provision. The school, serving over 1,700 students (55% boys and 45% girls), currently lacks functional sanitation facilities, access to clean drinking water, and hygiene infrastructure, resulting in widespread health issues, high absenteeism—particularly among girls—and significant barriers to quality education. The gap between the current condition and the desired standard is stark. In February 2024, the PMIC of Lazuli Pamir Consulting (PMIC) conducted a WASH Facility Rapid Assessment, supported by Focus Group Discussions (FGDs) and Key Informant Interviews (KIIs). The findings revealed: - 83% of existing latrines were non-functional or unsafe - 100% of students had no access to soap or handwashing stations - 37% of adolescent girls reported missing school due to lack of safe, gender-sensitive sanitation - WASH-related absenteeism contributes to over 25% of school absences Using Bradshaw’s Categories of Need, all four types are evident: - Felt Need: Students and parents expressed dissatisfaction with WASH conditions. - Expressed Need: School officials formally requested support. - Comparative Need: Peer schools with WASH access report higher attendance and fewer illnesses. - Normative Need (Selected): The school fails to meet national and international WASH standards, such as those defined by the Ministry of Education, UNICEF, and Sphere Standards. This professional, standards-based deficiency confirms the normative need as the strongest justification for intervention. The consequences of inaction are severe: continued student illness, preventable disease outbreaks, high dropout rates (especially among girls), violation of child protection standards, and widening gender disparities in education. This need is aligned with Sustainable Development Goals—particularly SDG 6 (Clean Water and Sanitation), SDG 4 (Quality Education), and SDG 5 (Gender Equality)—as well as Afghanistan’s National Education Strategic Plan and World Bank development priorities. The PMIC of Lazuli Pamir Consulting, with over two decades of operational presence and technical experience in WASH, education, and health in remote Afghan districts, is fully equipped and committed to addressing these urgent needs. Through this project, PMIC will deliver a targeted, evidence-based, and community-driven solution that bridges service gaps and fosters long-term positive change.

# Theory of Change:

If the World Bank provides funding, and the PMIC of Lazuli Pamir Consulting mobilizes its technical expertise, field teams, and community partnerships, then we will be able to construct gender-segregated latrines, install a solar-powered water system, build handwashing stations, deliver hygiene education to 1,700 students, train 25 school staff, and distribute hygiene kits. If these activities are implemented effectively, then the school will have safe, functional WASH infrastructure; students and staff will have increased knowledge and awareness of hygiene practices; and the school will have the capacity to maintain these facilities. If WASH facilities are available, accessible, and properly used, then students will adopt safer hygiene behaviors, leading to reduced incidence of hygiene-related illnesses, especially among girls. If students remain healthy and feel safe at school, then absenteeism will decline, especially for adolescent girls, and academic performance and engagement will improve. Ultimately, this will lead to a healthier, more inclusive, and equitable learning environment for all students at Zebak Secondary School. This change will occur assuming that the school leadership remains committed, local authorities cooperate, students and staff adopt the promoted behaviors, and there are no major disruptions to implementation due to conflict or natural disasters.

# Logical Framework:

Level; Description; Indicators; Means of Verification; Assumptions. Goal; Improved health, school attendance, and learning environment for students at Zebak Secondary School; - 30% reduction in hygiene-related illnesses among students - 20% increase in girls’ school attendance; - Clinic health records - School attendance registers - MoE monitoring reports. Outcome(s); - Functional, inclusive WASH infrastructure in place - Improved hygiene practices among students and staff - Reduced absenteeism, especially among girls; - 100% of school WASH facilities functional and accessible - 80% of students demonstrate correct handwashing technique - 25% decrease in WASH-related absenteeism; - Site inspection reports - Pre/post KAP (Knowledge, Attitude, Practice) surveys - School records; - Students and staff adopt hygiene behavior - Facilities maintained after handover. Outputs; - 12 gender-segregated latrines constructed- Solar-powered water system installed - Handwashing stations functional - 1,700 students trained in hygiene - 25 staff trained in WASH maintenance - Hygiene kits distributed; - # of latrines constructed (target: 12) - # of students receiving hygiene kits (target: 1,700) - # of trained teachers (target: 25); - Completion certificates - Distribution lists- Training attendance sheets - Construction progress reports; - Construction completed on time - Supplies and materials available locally. Activities; - Activity 1.1: Conduct site assessment and prepare architectural/technical designs - Activity 1.2: Procure construction materials and solar water system components - Activity 1.3: Construct 12 gender-segregated, child-friendly latrines - Activity 1.4: Install a solar-powered water pumping system with a raised storage tank - Activity 1.5: Connect water system to latrines and handwashing stations - Activity 2.1: Design and position handwashing station layout near latrines and classrooms - Activity 2.2: Construct handwashing stations with water connections - Activity 2.3: Install soap dispensers and ensure accessibility for all students - Activity 2.4: Test functionality and water flow consistency - Activity 3.1: Develop culturally appropriate hygiene education materials (posters, flipcharts) - Activity 3.2: Conduct interactive hygiene awareness sessions for all 1,700 students - Activity 3.3: Organize school-wide hygiene promotion campaigns and competitions - Activity 3.4: Monitor behavior change and reinforce key hygiene messages - Activity 4.1: Identify and select 25 relevant school staff (teachers, janitors, management) - Activity 4.2: Conduct hands-on training on sanitation facility maintenance - Activity 4.3: Provide WASH operation and maintenance manuals - Activity 4.4: Establish a facility management schedule with clear roles - Activity 5.1: Procure 1,700 hygiene kits (soap, toothbrush, toothpaste, towel, etc.) - Activity 5.2: Organize distribution event for students and ensure equitable access - Activity 5.3: Provide orientation on how to properly use and maintain hygiene items - Activity 5.4: Conduct post-distribution follow-up to assess usage and satisfaction; Inputs: - Construction Materials & Equipment (Cement, bricks, steel bars, pipes, sinks, taps, soap dispensers, solar water pump, storage tank) - Skilled & Unskilled Labor (Masons, plumbers, electricians, supervisors) - Technical Services (Engineering designs, WASH specialists, hygiene trainers, MEAL staff) - Training & Awareness Materials (Hygiene education kits, posters, manuals, flipcharts, handouts) - Hygiene Kits (Soap, toothbrush, toothpaste, towel, nail cutter) - Toolkits for Maintenance (Cleaning and minor repair tools for school staff) - Monitoring & Evaluation Tools (KAP survey forms, distribution checklists, training attendance sheets) - Transportation & Logistics (Vehicles for material and kit delivery, storage and packaging supplies) - Community Engagement Support (Mobilizers, communication materials, local facilitators) - Training Venue & Supplies (Stationery, flipcharts, refreshments for sessions); - Procurement records - Contractor agreements- Activity reports - PMIC monitoring data; - Community supports implementation - Security allows site access - Skilled labor is available.

# Target Beneficiaries:

Beneficiary Type; Gender; Age Group; Estimated Number. Total (Direct); M/F; 7 - 65; 1,750. Total (Indirect); M/F; 7 - 65; 9,307. Grand Total; M/F; 7 - 65; 11,057. Beneficiary Type; Group Description; Gender (M/F/Other); Age Group; Vulnerable Group (Y/N); Location; Estimated Number; Selection Criteria/Justification. Direct; Students enrolled at Zebak Secondary School; M/F; 7–18 years; Y; Zebak Secondary School, Badakhshan; 1,700; All students attending the school; directly affected by lack of WASH. Direct; Teachers and administrative staff; M/F; 22–60 years; N; Zebak Secondary School, Badakhshan; 40; School-employed personnel involved in education and hygiene promotion. Direct; Janitorial and support staff; M/F; 25–65 years; Y; Zebak Secondary School, Badakhshan; 10; Responsible for facility cleaning and maintenance. Indirect; Family members of students (7 per household); M/F; All age groups; Y; Zebak District; 9,187 (1,700 × 7) – 25%; Household members benefit from improved hygiene behavior at home. Indirect; School visitors and community users; M/F; Mixed; Y; Zebak Secondary School; 100; Occasional users of the facility during community or public events. Indirect; Health workers observing reduction in caseload; M/F; 25–60 years; N; Zebak District Health Centers; 20; Benefit from reduced school-related hygiene cases and outreach impact.

# Risk Analysis & Mitigation Plan:

S.N; Risk Category; Specific Risk; Likelihood; Impact; Mitigation Strategy; Responsible Actor(s). 1; Security; Armed conflict or insurgent activity disrupts project implementation; Low; High; Coordinate with local security forces; avoid high-risk periods; establish contingency plans; PMIC, Local Government, Security Agency. 2; Access & Logistics; Road inaccessibility during winter or heavy rainfall hampers material delivery; High; High; Schedule construction during dry months; pre-position materials; use local labor and transport; PMIC Logistics & Field Team. 3; Procurement; Delay in procurement of construction materials and hygiene kits; Medium; Medium; Initiate early procurement; work with pre-approved local suppliers; maintain buffer stock; PMIC Procurement & Logistics. 5; Staffing; Difficulty recruiting skilled labor in remote location; High; Medium; Provide incentives for staff; use local skilled workers where available; offer remote supervision; PMIC HR & Construction Supervisor. 6; Gender Sensitivity; Inadequate attention to privacy and dignity needs of girls; Low; High; Design gender-segregated, MHM-compliant toilets; engage female students in design feedback; PMIC Engineers, MEAL, Gender Focal Point. 7; Facility Maintenance; WASH infrastructure deteriorates due to lack of maintenance; Medium; High; Train janitors and teachers; assign maintenance roles; involve School Management Committee (SMC); School Management, PMIC Field Team. 8; Financial; Currency fluctuation or donor disbursement delay impacts budget; Medium; Medium; Use flexible procurement contracts; maintain contingency funds; regular coordination with donor; PMIC Finance, Donor Focal Point. 9; Monitoring & Evaluation; Inability to conduct frequent M&E due to remoteness or poor communication network; Medium; Medium; Use mobile-based data tools; assign local monitors; conduct quarterly field visits; PMIC MEAL Team. 10; Political/Administrative; Changes in local administration disrupt approvals or cooperation; Medium; Medium; Build relationships with multiple levels of government; ensure official MoUs are in place; PMIC Management & Advocacy Team.

# Detailed Budget Plan:

Direct Costs: Code; Budget Line Description; Unit Description; Unit Type; Unit Quantity; Unit Cost (USD); Duration; % Charged to Donor; Total Cost (USD). Output 1:. 1.1; Conduct site assessment and prepare architectural/technical designs; Design Package; Lot; 1; 5,000; 1 Month; 100%; 5,000. Remarks: Required to ensure accurate, safe, and context-appropriate WASH facility design.. 1.2; Procure construction materials and solar water system components; Construction Materials; Lot; 1; 10,000; 1 Month; 100%; 10,000. Remarks: Includes procurement of high-quality local materials, pipes, tanks, solar pumps, etc.. 1.3; Construct 12 gender-segregated, child-friendly latrines; Latrine Unit; Unit; 12; 5,000; 2 Months; 100%; 60,000. Remarks: Ensures dignity, privacy, and inclusiveness for boys and girls, compliant with SPHERE standards.. 1.4; Install a solar-powered water pumping system with a raised storage tank; Water System; System; 1; 45,000; 1 Month; 100%; 45,000. Remarks: Provides sustainable, off-grid water access, reducing operational costs and environmental impact.. 1.5; Connect water system to latrines and handwashing stations; Plumbing & Fittings; Lot; 1; 12,000; 1 Month; 100%; 12,000. Remarks: Ensures full functionality and usability of all sanitation facilities in the school compound.. Output 2:. 2.1; Design and position handwashing station layout near latrines and classrooms; Layout Design; Lot; 1; 4,500; 1 Month; 100%; 4,500. Remarks: Ensures ergonomic placement and user-friendly access, particularly for younger and female students.. 2.2; Construct handwashing stations with water connections; Handwashing Station; Unit; 6; 2,500; 1 Month; 100%; 15,000. Remarks: Builds durable stations with reliable water access to promote daily hygiene practices.. 2.3; Install soap dispensers and ensure accessibility for all students; Soap Dispenser; Unit; 20; 25; 1 Month; 100%; 500. Remarks: Provides essential hygiene tools and ensures inclusive use by students of all abilities.. 2.4; Test functionality and water flow consistency; Functionality Test; Activity; 1; 250; 1 Time; 100%; 250. Remarks: Verifies that stations are fully operational and water supply is consistent before handover.. Output 3:. 3.1; Develop culturally appropriate hygiene education materials (posters, flipcharts); Educational Kit; Set; 1; 1,000; 1 Month; 100%; 1000. Remarks: Ensures messages are age-appropriate, gender-sensitive, and locally relevant to maximize understanding.. 3.2; Conduct interactive hygiene awareness sessions for all 1,700 students; Awareness Session; Session; 10; 1,000; 1 Month; 100%; 10,000. Remarks: Engages students through participatory methods to internalize hygiene practices and reduce illness.. 3.3; Organize school-wide hygiene promotion campaigns and competitions; Campaign; Event; 2; 500; 1 Month; 100%; 1,000. Remarks: Promotes peer learning, motivation, and school-wide culture of cleanliness through fun and creativity.. 3.4; Monitor behavior change and reinforce key hygiene messages; Monitoring Visits; Visit; 3; 150; 1 Month; 100%; 450. Remarks: Tracks progress and ensures ongoing reinforcement of hygiene practices through regular field monitoring.. Output 4:. 4.1; Identify and select 25 relevant school staff (teachers, janitors, management); Staff Selection; Lot; 1; 750; 1 Time; 100%; 750. Remarks: Ensures proper selection of responsible individuals who will manage and maintain WASH facilities post-project.. 4.2; Conduct hands-on training on sanitation facility maintenance; Training Workshop; Session; 2; 500; 1 Month; 100%; 1000. Remarks: Equips staff with practical skills to ensure sustainability and functionality of WASH infrastructure.. 4.3; Provide WASH operation and maintenance manuals; Printed Manuals; Unit; 25; 50; 1 Month; 100%; 1,250. Remarks: Distributes easy-to-follow guides to support long-term upkeep of sanitation and water systems.. 4.4; Establish a facility management schedule with clear roles; Schedule Template; Lot; 1; 150; 1 Month; 100%; 150. Remarks: Defines roles and routines to ensure accountability and regular maintenance of installed facilities.. Output 5:. 5.1; Procure 1,700 hygiene kits (soap, toothbrush, toothpaste, towel, etc.); Hygiene Kit; Unit; 1,700; 10; 1 Month; 100%; 17,000. Remarks: Each kit includes essential hygiene items to promote daily hygiene habits among students.. 5.2; Organize distribution event for students and ensure equitable access; Distribution Event; Event; 1; 500; 1 Day; 100%; 500. Remarks: Event ensures all students receive kits fairly and promotes awareness of their importance.. 5.3; Provide orientation on how to properly use and maintain hygiene items; Orientation Session; Session; 2; 250; 1 Month; 100%; 500. Remarks: Sessions will guide students on correct usage to ensure maximum benefit and behavioral change.. 5.4; Conduct post-distribution follow-up to assess usage and satisfaction; Follow-up Survey; Activity; 1; 500; 1 Month; 100%; 500. Remarks: Follow-up ensures accountability, assesses impact, and identifies areas for improvement.. Total; 186,350. Indirect Costs Code; Budget Line Description; Unit Description; Unit Type; Unit Quantity; Unit Cost (USD); Duration; % Charged; Total Cost (USD). IC.1; Project management and supervision Covers PM salary, monitoring visits, coordination, and reporting.; Monthly Fee; Month; 12; 3,500; 12; 100%; 42,000. IC.2; Financial and audit support Covers financial reporting, bookkeeping, and independent audits to ensure transparency and compliance with donor requirements.; Service; Lot; 1; 1,000; 1; 100%; 1,000. IC.3; Administrative support and reporting Supports day-to-day coordination, documentation, and reporting to ensure smooth project operations and timely deliverables.; Admin Support; Month; 12; 2,500; 12; 100%; 30,000. Total:; 73,000. Cross-Cutting Activities: Code; Budget Line Description; Unit Description; Unit Type; Unit Quantity; Unit Cost (USD); Duration; % Charged; Total Cost (USD). CC.1; Gender, Disability & Child Safeguarding Measures Ensures inclusive access, protection, and participation of all students, especially girls, children with disabilities, and vulnerable groups.; Awareness Tools; Lot; 1; 5,000; 1; 100%; 5,000. CC.2; Environmental and Social Safeguards Compliance Mitigates environmental and social risks by ensuring construction and activities follow safe, sustainable, and ethical practices.; Audit & Training; Lot; 1; 5,000; 1; 100%; 5,000. CC.3; Community feedback and complaint handling mechanisms Promotes accountability and transparency by allowing beneficiaries to voice concerns, provide feedback, and report issues safely.; Setup & Tools; Lot; 1; 4,000; 1; 100%; 4,000. Total:; 14,000. Grant Total Project Budget: S.N; Budget Line Description; Unit Description; Unit Type; Unit Quantity; Unit Cost (USD); Duration; % Charged; Total Cost (USD). 1; Direct Costs; Lot; 1; 12; 100%; 186,350. 2; Contingency (5%): This reserve covers unforeseen costs such as minor price escalations, delays due to weather, logistics disruptions, or unexpected community needs—ensuring uninterrupted project implementation and risk mitigation.; Reserve Fund; Lot; 1; 9,300; 12; 100%; 9,300. 3; Indirect Costs; Lot; 1; 105,000; 12; 100%; 73,000. 4; Cross-Cutting Activities:; Lot; 1; 14,000; 12; 100%; `14,000. Total:; 282,650.

# Work Plan:

Activity; Month 1; Month 2; Month 3; Month 4; Month 5; Month 6; Month 7; Month 8; Month 9; Month 10; Month 11; Month 12. 1.1 Conduct site assessment and prepare architectural/technical designs; ✔. 1.2 Procure construction materials and solar water system components; ✔. 1.3 Construct 12 gender-segregated, child-friendly latrines; ✔; ✔; ✔; ✔. 1.4 Install solar-powered water pumping system with storage tank; ✔; ✔; ✔. 1.5 Connect water system to latrines and handwashing stations; ✔. 2.1 Design and position handwashing station layout; ✔. 2.2 Construct handwashing stations with water connections; ✔; ✔; ✔. 2.3 Install soap dispensers and ensure accessibility; ✔. 2.4 Test functionality and water flow consistency; ✔. 3.1 Develop hygiene education materials; ✔. 3.2 Conduct hygiene awareness sessions for 1,700 students; ✔. 3.3 Organize hygiene promotion campaigns; ✔. 3.4 Monitor behavior change and reinforce messages; ✔; ✔; ✔; ✔; ✔; ✔. 4.1 Identify and select 25 school staff; ✔. 4.2 Conduct training on sanitation facility maintenance; ✔. 4.3 Provide WASH operation and maintenance manuals; ✔. 4.4 Establish facility management schedule; ✔. 5.1 Procure 1,700 hygiene kits; ✔; ✔; ✔. 5.2 Organize distribution event; ✔. 5.3 Provide orientation on hygiene item use; ✔. 5.4 Conduct post-distribution follow-up; ✔; ✔. IC.1 Project management and supervision; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔. IC.2 Financial and audit support; ✔. IC.3 Administrative support and reporting; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔. CC.1 Gender, Disability & Child Safeguarding Measures; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔. CC.2 Environmental and Social Safeguards Compliance; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔. CC.3 Community feedback and complaint handling mechanisms; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔; ✔. Close-out Activities; ✔.

# Monitoring, Evaluation, Accountability & Learning (MEAL) Plan:

The MEAL strategy for this project is designed to ensure systematic measurement of results, inclusive accountability, and adaptive learning throughout the implementation cycle. It supports effective decision-making, transparency, and continuous improvement in line with the Core Humanitarian Standard (CHS) and SPHERE Minimum Standards. 1. Indicators, Data Sources, and Frequency Result Level; Indicators; Data Sources; Frequency; Tools. Goal; - 30% reduction in hygiene-related illnesses among students - 20% increase in girls’ school attendance; - Clinic health records - School attendance registers; Baseline and Endline; Clinic data form MoE records. Outcomes; - 100% of WASH facilities functional - 80% of students demonstrate correct handwashing - 25% decrease in WASH-related absenteeism; - Inspection reports - KAP surveys - School records; Midline and Endline; Facility checklist KAP survey tools. Outputs; - 12 latrines constructed - 1,700 students trained - 25 staff trained - Hygiene kits distributed; - Training attendance sheets - Distribution records - Progress reports; Monthly/Quarterly; Distribution checklists Training logs. Process; - % of planned activities completed on time - # of community engagement sessions held; - Field reports - Activity logs; Monthly; Project tracker Mobilizer reports. All indicators will be disaggregated by gender, age, and disability status, where applicable, to monitor equitable outcomes. 2. Data Collection and Quality Assurance - Baseline and Endline KAP Surveys will be administered to assess knowledge, attitudes, and practices related to hygiene. - Routine site monitoring visits will be conducted by PMIC’s MEAL staff using digital tools (e.g., KoboToolbox or ODK) to track construction progress and behavioral outcomes. - Data will be validated through triangulation with focus group discussions (FGDs), key informant interviews (KIIs), and school records. 3. Community Feedback, Accountability, and Complaints Handling The project will implement inclusive and safe feedback mechanisms to ensure community voices guide implementation and course corrections: - Suggestion boxes installed at the school and DEO office. - Community hotlines managed by MEAL staff to allow confidential reporting. - Quarterly community meetings with students, parents, and teachers to discuss progress and challenges. - All feedback and complaints will be logged, reviewed biweekly, and addressed using PMIC’s Accountability Framework, ensuring timely and respectful resolution. - Child-friendly communication channels will be integrated to enable safe feedback from students, especially girls. 4. Learning and Adaptive Management - Quarterly reflection sessions with the implementation team will be held to review data, challenges, and success stories. - After-Action Reviews (AARs) at midline and endline will facilitate organizational learning and allow adaptations in real time. - Lessons learned will be documented in the final project report and shared with the World Bank, the Ministry of Education, and the WASH Cluster (if active) to inform future programming. - Learning products such as case studies, human-interest stories, and photo narratives will be developed and disseminated to enhance visibility and replication of best practices.

# Sustainability & Exit Strategy:

The long-term sustainability of this project is embedded in its design and implementation approach, with a focus on community ownership, government responsibility, institutional capacity building, and strategic planning for a smooth handover and exit. Government Involvement and Institutional Ownership: Zebak Secondary School is a government-registered school under the Ministry of Education. From inception, the project will be implemented in close coordination with the District Education Office (DEO) and the Badakhshan Provincial Education Directorate to ensure alignment with public education priorities and sector plans. - Upon project completion, the entire WASH infrastructure will be formally handed over to the Government of Afghanistan through the DEO. - A handover agreement will be signed, clearly outlining responsibilities for operation, routine maintenance, and budgeting for consumables (e.g., soap, cleaning supplies). Community Ownership and Engagement: Community involvement will be fostered throughout the project to build a sense of shared responsibility: - The School Management Committee (SMC), which includes parent and community representatives, will be engaged in design validation, implementation oversight, and post-project maintenance planning. - Hygiene awareness activities will instill a culture of cleanliness, responsibility, and peer accountability among students and teachers. - The SMC will also be trained to monitor facility use, mobilize resources locally, and coordinate with the DEO when repair or replenishment needs arise. Capacity Building for Sustainability: To ensure long-term functionality: - 25 school staff (including janitors, teachers, and administrators) will receive hands-on training in sanitation facility maintenance, hygiene promotion, and minor repairs. - The project will develop and distribute user-friendly maintenance manuals and establish a facility management schedule assigning specific roles to school personnel. - Janitorial staff will be provided with basic toolkits and cleaning supplies at handover. Resource Mobilization and Support: - The DEO will be encouraged to include WASH maintenance costs in its annual operational budget for the school. - The project will explore the possibility of establishing a small maintenance fund through community contributions or parent-teacher associations to cover minor repairs post-handover. Exit Timeline and Handover Plan: - Final quarter of the implementation period (Months 10–12) will focus on transition, including: - Final review of construction quality - Capacity assessment of school staff - Refresher training sessions - Joint inspections with DEO officials - A formal handover ceremony will be held at the end of Month 12, with signed documentation, asset transfer records, and commitment letters from school and government representatives.

# Gender, Protection, and Inclusion Strategy:

This project is guided by a strong commitment to equity, dignity, and inclusion. All activities are designed and implemented in line with international humanitarian standards, including the SPHERE Standards, Core Humanitarian Standard on Quality and Accountability (CHS), and PMIC’s institutional policies on child safeguarding, gender equality, and disability inclusion. Equitable Participation and Benefits for All: - Gender Equity: The project ensures equitable access to WASH facilities and services for all students regardless of gender, with a special focus on girls’ needs during menstruation. Twelve gender-segregated latrines will be constructed, each equipped with Menstrual Hygiene Management (MHM) features such as water, bins, and privacy-supporting infrastructure. - Inclusive Participation: Design and implementation processes will involve active consultation with girls, female teachers, persons with disabilities, and marginalized families through Focus Group Discussions (FGDs), participatory planning, and community forums. - Equitable Resource Allocation: Hygiene kits will be distributed to all 1,700 students, with tailored guidance for vulnerable groups to ensure they can fully benefit from the materials. Protection Measures: - Do No Harm Principle: The project adheres to the principle of Do No Harm, ensuring that interventions do not unintentionally cause exclusion, stigmatization, or security risks. All physical infrastructure will be designed and located to maximize safety, privacy, and accessibility, especially for girls and children with disabilities. - Child Safeguarding: PMIC’s Child Protection and Safeguarding Policy will guide all interactions with students. Staff and contractors will be trained to recognize, prevent, and report abuse or misconduct. Latrines and hygiene areas will include well-lit, secure spaces to reduce risks of harassment or abuse. - Gender-Based Violence (GBV) Risk Reduction: The project proactively addresses GBV risks by: - Designing private, secure latrines for girls - Engaging female staff in community consultations - Training field staff on gender sensitivity, safe referral pathways, and survivor-centered approaches - Ensuring confidential reporting mechanisms are available for all participants Disability Inclusion: - All WASH infrastructure will comply with universal design principles to accommodate children and staff with physical or sensory disabilities. - Hygiene education sessions and materials will be adapted to be visually and audibly accessible, using illustrations, inclusive language, and participatory teaching methods. - Site layouts and facilities will include ramps, grab bars, and non-slip flooring to ensure ease of access. Accountability and Monitoring: - The project will use disaggregated indicators (by gender, age, and disability status) to measure reach and equity of service delivery. - Feedback and complaints mechanisms (e.g., suggestion boxes, hotline numbers, FGDs) will be anonymous, inclusive, and accessible for all beneficiaries, including children and persons with disabilities. - Lessons learned from inclusive practices will be documented and shared with stakeholders, contributing to continuous learning and improvement.

# Implementation and Coordination Arrangements:

The implementation of the WASH Infrastructure Improvement and Hygiene Awareness Project at Zebak Secondary School will be led by the PMIC of Lazuli Pamir Consulting – Afghanistan (PMIC-A), in close coordination with school authorities, community structures, and relevant government bodies. A multi-layered operational structure, strong coordination mechanisms, and clear communication channels will ensure effective project delivery, accountability, and sustainability. Operational Setup and Team Structure: The project will be implemented under the leadership of PMIC’s WASH Program Unit, based in Kabul and Badakhshan, with the following structure: - Project Manager (Eng. Zohra Amiri) – overall project coordination, donor engagement, and reporting. - MEAL Specialist (Dr. Faridullah Naeem) – monitoring, evaluation, and learning. - Gender and Inclusion Advisor (Ms. Laila Habibi) – safeguarding, gender-sensitive implementation, and inclusion strategies. - Field Engineers and Construction Supervisors – responsible for day-to-day construction oversight, quality control, and progress monitoring. - Community Mobilizers – ensure consistent engagement with local stakeholders and promote ownership. The implementation team will work in tandem with school management, janitorial staff, and teachers trained in WASH maintenance to ensure operational integration and sustainability at the school level. Government and Stakeholder Coordination: The project will align with national and subnational policies and will actively coordinate with: - District Education Office (DEO) and Badakhshan Provincial Education Directorate – for formal approvals, alignment with education sector plans, and integration into the school improvement framework. - Ministry of Public Health (MoPH) (as required) – to ensure consistency with public health and hygiene standards. - WASH Cluster (if active) – for technical guidance, updates, and coordination with other WASH actors in the region. - Community-Based Structures, such as the School Management Committee (SMC) and Community Development Councils (CDCs) – to ensure local participation, feedback, and oversight. Monthly coordination meetings will be organized involving all relevant stakeholders, including government, donors, and community representatives, to review progress, resolve bottlenecks, and validate decisions. Community Engagement and Participation: The project embeds community engagement throughout its lifecycle: - Participatory Design: Community members, especially girls and female teachers, will be involved in the WASH facility design phase to ensure privacy and inclusivity. - Awareness Campaigns: Regular hygiene promotion campaigns and school-wide events will foster a culture of cleanliness and responsibility. - Feedback Mechanisms: Beneficiaries will be encouraged to provide input via suggestion boxes, hotlines, and structured feedback tools managed by the MEAL team. - Sustainability Measures: Community volunteers and parents will be engaged in light maintenance, awareness reinforcement, and protection of facilities. Decision-Making, Reporting, and Communication Channels: - Decision-Making: Strategic decisions will be made by the PMIC Project Steering Committee, which includes the Project Manager, Finance Officer, and Senior Technical Advisors. Day-to-day operational decisions will be managed by the Field Implementation Team. - Reporting: PMIC will provide monthly progress reports, quarterly technical updates, and a final completion report to the World Bank and other relevant stakeholders. Reports will include quantitative results, challenges, lessons learned, and photos. - Communication Channels: - Internal: Weekly coordination calls between field teams and Kabul HQ. - External: Bi-weekly email updates to stakeholders and periodic review meetings (virtual or in-person) with the World Bank team. - Community: On-site notice boards, SMS announcements (where feasible), and community forums will be used to ensure transparent communication.

# Annexes / Appendices:

- Organizational Registration & Legal Documents - Past Project Summaries / References - Maps and Technical Drawings (if applicable) - Detailed Budget Breakdown (Excel format if required) - Letters of Support - Staff CVs / Organizational Chart / Staffing Plan - MEAL Tools / Templates / Indicator Tracking Table (ITT) - Procurement Plan - Environmental and Social Safeguards / Do No Harm Statement - Community Consultation / Needs Assessment Summary Report - Photographs (before/after or current site conditions) - Security Plan (for fragile areas) - Audit Reports or Financial Statements (last 1–2 years) - Donor Compliance Checklist (if applicable) - Child Protection Policy / Safeguarding Policy - Anti-Fraud, Code of Conduct, or Ethical Guidelines - Logistics or Supply Chain Plan - Environmental and Social Safeguards Policy - Financial Management and Controls Policy - Procurement Policy - Occupational Health and Safety (OHS) Policy - Community Engagement and Participation Policy - Monitoring, Evaluation, Accountability and Learning (MEAL) Policy