Advance Report Writing Guideline

1. Executive Summary

A concise overview of the report’s purpose, highlights, achievements, challenges, and key recommendations.

2. Background / Project Overview

Context of the project: location, target population, rationale, donor, objectives, and implementation timeline.

3. Objectives and Expected Outcomes

A list of the project’s goals and specific measurable results (outputs/outcomes/impact) as per the logical or results framework.

4. Activities Implemented

Detailed description of what was carried out during the reporting period, including dates, locations, and responsible teams.

5. Achievements vs. Planned Results

Comparison of planned targets with actual achievements, usually presented in table or matrix format.

6. Monitoring and Evaluation (M&E)

Data collection methods, KPIs, tools used, M&E findings, and insights on progress and effectiveness.

7. Challenges and Lessons Learned

Barriers faced, reasons for delays or underachievement, and adaptive strategies taken or recommended.

8. Beneficiary Feedback and Participation

Feedback from the community, direct and indirect beneficiaries, and evidence of participatory approaches.

9. Risk Management and Mitigation

Risks identified (security, political, operational), their likelihood/impact, and how they were or will be mitigated.

10. Cross-Cutting Issues

Integration of gender, disability inclusion, environmental safeguards, child protection, and accountability mechanisms.

11. Coordination and Partnerships

Coordination efforts with local government, NGOs, donors, and community actors. Summary of meetings or joint efforts.

12. Financial Report

Summary of budget vs. actual expenditure, burn rate, and explanation of variances. May include tables and graphs.

13. Case Studies / Human Stories

Short stories or profiles illustrating the project’s impact on individuals or communities.

14. Visual Documentation

Photos, charts, graphs, maps showing progress, construction, distributions, trainings, or community engagement.

15. Recommendations and Way Forward

Proposals for next steps, adjustments needed, areas for improvement, and strategic direction for continuation or scale-up.