Grant Proposal

Project Title: Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District

Grant ID: 0124512120

Submitted by PMIC-NGO

Contact Details:

Email: pmic@lazulipamir.com

Phone: 0749055531

Website: www.lazulipmic.com

Submitted to: UNICEF, Afghanistan

Address: Jalalabad Road, Kabul, Afghanistan

Date and Time: 30 January 2025 1600 Hr

Contents

Cover Letter	3

Organizational Information	4

Statement of Need	6

Executive Summary	10

Project Objectives	13

Target Population/Beneficiaries	16

Organizational Capacity	18

Work Plan:	22

Risk Assessment:	23

Budget Breakdown	25

Sustainability Plan	26

MEAL Plan	31

Supporting Documents	36

Grant Proposal Submission Checklist	38

# Cover Letter

Abdul Rahman Sadiqi
PMIC, Lazuli Pamir Consulting
Email: PMIC@lazulipamir.com
Phone: +93 749 055 531
Website: www.PMIC.net

Date: January 30, 2025

To: UNICEF Afghanistan
Jalalabad Road
Kabul, Afghanistan

Subject: Submission of Grant Proposal for "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District"

Dear Sir/Madam,

On behalf of Project Management Initiatives Center (PMIC), I am pleased to submit our grant proposal for the project titled "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District." This initiative is aligned with UNICEF’s mission to improve access to clean water, sanitation, and hygiene, especially in underserved communities.

The proposed project addresses critical challenges faced by residents of Baharak District, where over 70% of households lack access to clean water and proper sanitation facilities. Our initiative aims to construct essential WASH infrastructure, conduct hygiene education programs, and empower communities for sustainable development.

PMIC has a strong track record of implementing impactful community development projects in Afghanistan. With our experienced team, robust operational framework, and commitment to transparency, we are confident in delivering measurable results that align with UNICEF's strategic priorities.

Thank you for considering this proposal. We appreciate the opportunity to partner with UNICEF in advancing sustainable development in Afghanistan. Please do not hesitate to contact us for additional information or clarification.

Sincerely,

# Organizational Information

- Name and Details

  - Full legal name: Project Management Initiatives Center NGO

  - Acronym: PMIC

  - Website: www.lazulipmic.com

  - Social Media Links: [Include links to LinkedIn, Twitter, Facebook, etc.]

- Mission and Vision

  - Mission: To enhance project management capabilities and implement sustainable development projects that improve the quality of life in underserved communities.

  - Vision: To be a leading consulting firm in project management and infrastructure development, ensuring equitable access to essential services in Afghanistan and beyond.

- Legal Information

  - Registration Number: [12345]

  - Legal Status: Registered NGO Firm

  - Country of Registration: Afghanistan

  - Tax ID: [0123456789]

- Organizational Structure

  - Leadership: CEO, Program Director, Project Managers

  - Governance: Board of Directors overseeing strategic decisions

  - Key Personnel: Project Managers, Engineers, Financial Analysts, Trainers

- Areas of Expertise

  - Focus Sectors:

    - Education

    - Health

    - Water, Sanitation, and Hygiene (WASH)

    - Infrastructure Development

    - Capacity Building & Training

  - Regions of Operation: Afghanistan (nationwide) with international partnerships

- Track Record

  - Successful implementation of community-based development projects

  - Partnerships with international donors such as UNICEF, ADB, and UNDP

  - Proven impact in WASH, education, and infrastructure sectors

- Capacity

  - Highly qualified personnel with expertise in project management, engineering, and capacity building

  - Established infrastructure and logistical capabilities for project execution

  - Advanced financial and operational systems ensuring transparency and efficiency

- Financial Transparency

  - Strong financial management system adhering to international standards

  - Regular financial audits conducted by certified firms

  - Compliance with donor and regulatory financial reporting requirements

- Contact Information

  - Address: Jalalabad Road, Kabul, Afghanistan

  - Phone: +93 749 055 531

  - Email: PMIC@lazulipamir.com

  - Website: www.lazulipmic.com

  - Point of Contact: Abdul Rahman Sadiqi, Program Director

# Statement of Need

- Needs Assessment for a Proposal: A needs assessment identifies the problem that our project seeks to address, providing an evidence-based justification for its importance. In Baharak District, waterborne diseases are prevalent due to limited access to clean drinking water and inadequate sanitation facilities. Poor hygiene practices further intensify the situation, especially among children and vulnerable populations. The project aims to mitigate these health risks by developing sustainable water and sanitation solutions. This assessment is supported by statistical data, community feedback, and reports from health and humanitarian organizations. By focusing on clean water supply and hygiene promotion, this project aligns with global development priorities and UNICEF’s mission to improve health and living conditions. Ensuring access to safe drinking water and proper sanitation will reduce disease outbreaks and enhance community resilience.

- Context and Background: Baharak District, located in a remote part of Afghanistan, faces significant challenges due to inadequate infrastructure and poor public services. Limited access to safe drinking water and sanitation facilities has led to an increase in waterborne illnesses such as diarrhea and cholera, unreasonably affecting children. Economic conditions remain fragile, with many families relying on agriculture for survival, yet frequent droughts make water scarcity a persistent issue. Socially, the lack of awareness about hygiene and sanitation further aggravates health risks, leading to high rates of preventable diseases. Addressing these issues requires a holistic approach that combines infrastructure development with community engagement and education. Our project seeks to install water supply systems, construct sanitation facilities, and implement hygiene awareness programs to create long-term, sustainable solutions. By addressing these critical gaps, we aim to improve the quality of life and health outcomes for thousands of residents in Baharak District.

- Data Collection Methods: Our project’s needs assessment is based on a combination of primary and secondary data sources. Surveys and focus group discussions were conducted within the Baharak community to understand the most pressing water and sanitation challenges. These surveys gathered input from households, school administrators, and local healthcare workers to determine current hygiene practices and gaps in services. Additionally, government reports and data from humanitarian organizations such as UNICEF and WHO were analyzed to establish baseline statistics. Secondary research helped cross-validate our findings, ensuring an evidence-based approach to project planning. The data collection process also involved collaboration with local authorities to align our project’s objectives with regional development plans. The gathered data confirmed the urgent need for improved water and sanitation infrastructure, reinforcing the project’s significance. By using both qualitative and quantitative methods, our approach ensures a well-informed strategy for addressing water and hygiene deficiencies in Baharak District.

- Key Findings: The assessment revealed that over 70% of households in Baharak lack access to safe drinking water, with many relying on untreated surface water. Additionally, 65% of reported illnesses in the district are waterborne, affecting children and the elderly the most. Schools and healthcare centers are particularly affected, with insufficient sanitation facilities leading to increased absenteeism due to illness. Women and children spend significant portions of their day collecting water from distant sources, reducing time available for education and income-generating activities. Community engagement sessions highlighted that many residents are unaware of best hygiene practices, further contributing to the spread of disease. Addressing these issues requires not only infrastructure improvements but also behavioral change programs. By implementing targeted interventions, we can reduce disease prevalence, improve educational outcomes, and enhance the overall well-being of the community.

- Problem Statement: The lack of access to clean water and sanitation in Baharak District represents a serious public health issue. The existing water sources are either contaminated or located far from residential areas, making them unreliable for daily use. Due to poor sanitation, open defecation remains common, intensifying health risks. The absence of effective waste management systems leads to water contamination, further deteriorating community health. This problem is not only a health crisis but also an economic burden, as families frequently incur medical expenses due to preventable diseases. Schools without proper sanitation facilities see higher dropout rates, especially among girls. Resolving these issues requires a multi-faceted approach that includes infrastructure, education, and community involvement. By investing in water supply systems and hygiene programs, this project will ensure a healthier future for the people of Baharak District.

- Gap Analysis: The gap analysis identifies the disparity between the current situation and the desired state in Baharak District’s WASH sector. Presently, access to clean water and adequate sanitation facilities is severely limited, with over 70% of households relying on contaminated sources. Schools and healthcare centers lack proper sanitation, leading to heightened risks of waterborne diseases. The desired outcome is a district where every household, school, and health facility has sustainable access to clean water and improved hygiene facilities. Bridging this gap requires targeted interventions such as the construction of water supply systems, improved sanitation infrastructure, and community-led hygiene awareness programs. The key barriers include inadequate funding, lack of technical expertise, and social resistance to adopting better hygiene practices. By addressing these gaps with a well-structured intervention, this project will significantly improve health outcomes and quality of life in the region.

- Relevance to Donor/Stakeholder Goals: This project aligns with UNICEF’s core mission to improve access to clean water, sanitation, and hygiene, especially in underserved communities. The initiative directly supports Sustainable Development Goals (SDGs) 3 (Good Health and Well-being) and 6 (Clean Water and Sanitation). By providing sustainable WASH infrastructure and hygiene education, the project contributes to UNICEF’s objectives of reducing child mortality caused by waterborne diseases. The intervention also aligns with national development policies, ensuring long-term sustainability through community engagement and government collaboration. Stakeholders, including local authorities and community leaders, will play a crucial role in project implementation, ensuring local ownership and continued impact. This alignment with donor and stakeholder goals strengthens the project's feasibility and enhances its potential for long-term success.

- Recommendations/Solutions:

To achieve sustainable improvements in water and sanitation access, the following actionable steps are recommended:

- Infrastructure Development:

  - Constructing new water supply systems in underserved areas.

  - Building gender-sensitive latrines in schools and healthcare facilities.

  - Installing handwashing stations in public areas to promote hygiene.

- Capacity-Building Initiatives:

  - Training local water committees to manage and maintain WASH facilities.

  - Conducting hygiene education sessions targeting schoolchildren and families.

  - Providing technical training for local engineers and plumbers to ensure sustainable maintenance.

- Community Engagement Strategies:

  - Organizing awareness campaigns on the importance of hygiene and sanitation.

  - Encouraging community participation in WASH facility maintenance.

  - Partnering with local leaders to drive behavioral change initiatives.

- Conclusion:

The need for improved WASH infrastructure in Baharak District is urgent. The current lack of clean water and proper sanitation facilities has resulted in increased cases of waterborne diseases, affecting the health, education, and economic well-being of the community. Addressing this issue through infrastructure development, capacity-building, and community engagement will create lasting positive change. By ensuring access to clean water and better sanitation, this project will enhance health outcomes, improve school attendance, and reduce healthcare costs. The strong alignment with donor priorities, coupled with a well-structured implementation plan, makes this project a viable and impactful investment. With UNICEF’s support, we can bring sustainable improvements to the WASH sector in Baharak District, fostering a healthier and more resilient community.

# Executive Summary

1. Introduction:

The "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District" project seeks to address critical water, sanitation, and hygiene (WASH) challenges faced by the district's population. The lack of access to clean water and adequate sanitation infrastructure has led to increased cases of waterborne diseases, affecting the health and well-being of vulnerable groups, particularly women and children. This proposal outlines a comprehensive intervention that aligns with UNICEF’s mission to improve public health through sustainable WASH solutions. By addressing key infrastructural gaps and promoting hygiene awareness, the project will significantly enhance the quality of life for thousands of residents in Baharak District.

2. Objectives:

The primary objectives of this project are:

- Improve Water Access: Construct and rehabilitate water supply systems to ensure a clean and reliable source of drinking water.

- Enhance Sanitation Infrastructure: Build gender-sensitive latrines in schools and healthcare centers to promote hygiene and dignity.

- Promote Hygiene Awareness: Conduct community education programs to encourage sustainable hygiene practices.

- Empower Community Ownership: Train local committees for sustainable maintenance and governance of WASH facilities.

These objectives align with Sustainable Development Goals (SDGs) 3 (Good Health and Well-being) and 6 (Clean Water and Sanitation) while supporting Afghanistan’s national development priorities.

3. Approach/Methodology:

The project will be implemented in multiple phases to ensure sustainability and efficiency:

- Baseline Assessment: A comprehensive baseline assessment will be conducted to evaluate the current state of WASH infrastructure and services in Baharak District. This will involve field surveys, data collection, and consultations with local stakeholders, including community leaders, government representatives, and healthcare professionals. The assessment will identify key gaps, such as the number of households without access to clean water and schools lacking proper sanitation facilities. Understanding the socio-economic and environmental factors influencing hygiene behaviors will help design targeted interventions. The findings will be documented and serve as a foundation for project planning, implementation, and impact evaluation.

- Infrastructure Development This phase will focus on constructing new water supply systems, rehabilitating existing ones, and building sanitation facilities, including gender-sensitive latrines and handwashing stations. The infrastructure will be designed to withstand environmental factors and ensure long-term functionality. Key locations such as schools, healthcare centers, and densely populated areas will be prioritized. The project will employ local labor and materials wherever possible to stimulate economic activity in the community. Additionally, water purification units and waste management solutions will be integrated to enhance overall hygiene and health outcomes.

- Capacity-Building and Training To ensure long-term sustainability, capacity-building initiatives will be conducted for local stakeholders. Training sessions will be provided for school staff, healthcare workers, and community members on water resource management, sanitation maintenance, and hygiene promotion. Special focus will be placed on training local water committees responsible for facility upkeep. Workshops and practical demonstrations will be conducted to reinforce best practices. These efforts will enhance local knowledge and create a self-sustaining system where communities take ownership of their WASH facilities.

- Community Engagement Successful WASH interventions require active community participation. This phase will involve mobilizing residents through awareness campaigns, school programs, and local advocacy initiatives. Interactive sessions will address common misconceptions about hygiene, water use, and disease prevention. Community-led discussions will encourage behavior change, ensuring the long-term adoption of improved hygiene practices. The engagement strategy will include posters, radio announcements, and social media outreach to reach a broader audience. By involving the community at every stage, the project aims to foster a sense of ownership and collective responsibility.

- Monitoring and Evaluation A robust monitoring and evaluation (M&E) framework will be established to assess project effectiveness and impact. Key performance indicators will be developed to track improvements in water access, hygiene behavior changes, and reductions in waterborne diseases. Regular field visits and progress assessments will be conducted, ensuring accountability and transparency. Feedback mechanisms will be incorporated to address community concerns and adapt strategies as needed. Data collected through surveys and reports will be shared with stakeholders, including UNICEF, to demonstrate measurable progress and inform future interventions.

# Project Objectives

The “Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District” project is designed to address critical gaps in water, sanitation, and hygiene (WASH) infrastructure and practices, directly improving health outcomes and quality of life for 15,000 residents. Grounded in the SMART framework (Specific, Measurable, Achievable, Relevant, Time-Bound), the objectives below outline actionable, results-oriented goals aligned with UNICEF’s mission and Sustainable Development Goals (SDGs) 3 (Good Health) and 6 (Clean Water and Sanitation).

1. Improve Access to Safe Drinking Water

Specific: Construct 15 solar-powered water supply systems in underserved villages, prioritizing areas where 70% of households currently rely on contaminated surface water.

Measurable: Provide 5,000 households (30,000 liters/day) with clean water, verified through water quality testing and usage surveys.

Achievable: Utilize local labor and partnerships with Afghan engineering firms to ensure technical feasibility.

Relevant: Aligns with UNICEF’s mandate to reduce waterborne diseases and SDG 6.1 (universal access to safe water).

Time-Bound: Complete construction and operationalize systems within 18 months (by June 2026).

2. Enhance Sanitation Infrastructure

Specific: Build 300 gender-segregated latrines in 20 schools, 5 healthcare centers, and high-density residential areas to eliminate open defecation.

Measurable: Ensure 100% of target institutions have functional latrines, directly benefiting 3,000 students and 10,000 community members.

Achievable: Collaborate with local authorities to secure land and materials, adhering to WHO sanitation standards.

Relevant: Supports SDG 6.2 (adequate sanitation for all) and reduces school absenteeism, particularly among girls.

Time-Bound: Complete construction and launch hygiene signage campaigns by December 2025.

3. Promote Sustainable Hygiene Practices

Specific: Train 50 community health workers and 100 teachers to deliver hygiene education programs on handwashing, waste management, and disease prevention.

Measurable: Reach 80% of households (12,000 residents) through monthly workshops and school curricula, monitored via pre- and post-training knowledge assessments.

Achievable: Leverage PMIC’s existing networks with local NGOs to recruit and train facilitators.

Relevant: Addresses the root cause of poor hygiene practices linked to 65% of waterborne illnesses in Baharak.

Time-Bound: Conduct training within 6 months (by December 2024); sustain education campaigns for 24 months.

4. Empower Community-Led Sustainability

Specific: Establish 20 local water committees (1 per village) responsible for maintaining WASH infrastructure.

Measurable: Ensure 90% of committees demonstrate proficiency in system repairs and financial management through biannual audits.

Achievable: Provide 6-month technical training for 60 committee members, with PMIC mentorship for 12 months post-training.

Relevant: Ensures long-term functionality of infrastructure, aligning with UNICEF’s emphasis on community ownership.

Time-Bound: Form committees by March 2025; achieve full operational independence by June 2026.

5. Reduce Waterborne Disease Prevalence

Specific: Decrease diarrheal and cholera cases by 50% through improved WASH access and hygiene education.

Measurable: Track disease incidence via monthly health facility reports and community surveys.

Achievable: Partner with local clinics to distribute water purification tablets and conduct health screenings.

Relevant: Directly contributes to SDG 3.3 (combat communicable diseases) and reduces household healthcare costs by 30%.

Time-Bound: Achieve target reduction within 24 months of project launch (by January 2027).

Alignment with Stakeholder Priorities

These objectives reflect UNICEF’s strategic focus on equitable WASH access and resilience-building in conflict-affected regions. By addressing infrastructure gaps, behavioral change, and institutional capacity, the project ensures alignment with Afghanistan’s National Development Plan and global SDG targets. Transparent monitoring mechanisms, including third-party evaluations and real-time data sharing with UNICEF, will demonstrate accountability and impact.

Conclusion

The above objectives translate the urgent needs of Baharak District into actionable, time-bound interventions. By combining infrastructure development with community empowerment and education, the project ensures sustainable improvements in health, education, and economic stability. Clear metrics and adherence to SMART principles not only enhance donor confidence but also create a replicable model for future WASH initiatives in Afghanistan. With UNICEF’s support, this project will catalyze lasting change, transforming Baharak into a benchmark for rural WASH success.

# Target Population/Beneficiaries

The proposed project "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District" aims to benefit the most vulnerable communities in Baharak District, primarily focusing on underserved households, schoolchildren, and healthcare facility users. The project is designed to ensure equitable access to clean water and improved sanitation services, directly impacting the health and well-being of thousands of residents.

Primary Beneficiaries

- Households: Approximately 3,500 households (around 21,000 individuals) in Baharak District lack access to clean drinking water and proper sanitation. These families rely on unsafe water sources, exposing them to waterborne diseases.

- Children in Schools: Around 4,500 students across 12 schools will benefit from improved sanitation facilities, reducing absenteeism due to hygiene-related illnesses and ensuring a healthier learning environment.

- Healthcare Facilities: Five healthcare centers in the district serve over 8,000 patients annually. Improved water supply and hygiene measures will enhance patient care and reduce infection risks.

- Women and Girls: Women and girls bear the responsibility of water collection and are disproportionately affected by poor sanitation facilities. Gender-sensitive WASH interventions will significantly improve their daily lives, dignity, and safety.

- Local Communities: The project will engage community-based water management groups, ensuring the sustainability of WASH infrastructure and promoting long-term behavioral change.

Secondary Beneficiaries

- Local Government & Health Workers: Training in hygiene and sanitation management will strengthen local capacity to maintain and oversee the new infrastructure.

- WASH Committees: Community representatives will be trained to monitor and sustain water and sanitation systems.

- Local Laborers & Technicians: Employment opportunities will be created through construction, maintenance, and training initiatives.

This project aligns with Sustainable Development Goals (SDG) 3 (Good Health and Well-being) and SDG 6 (Clean Water and Sanitation), ensuring long-term community resilience and health improvement.

Estimated Beneficiaries Breakdown

| Category | Estimated Number of Beneficiaries |
| --- | --- |
| Households | 21,000 individuals (3,500 households) |
| Schoolchildren | 4,500 students (12 schools) |
| Healthcare facility users | 8,000 patients (5 centers) |
| Women & girls (special focus) | 10,000 individuals |
| Local WASH committees | 50 trained representatives |
| Health & government workers | 200 personnel |
| Local laborers/technicians | 100+ workers engaged |

This initiative will create a significant and lasting impact on Baharak District by improving health outcomes, reducing disease prevalence, and fostering a culture of hygiene and sanitation. The project will ensure sustainability through capacity-building efforts and community engagement.

# Organizational Capacity

Introduction

Project Management Initiatives Center(PMIC), has a proven track record in implementing water, sanitation, and hygiene (WASH) projects in Afghanistan. As a PMI Authorized Training Partner (ATP) and a recognized development consultancy, our organization possesses the expertise, resources, and strategic partnerships necessary to ensure the successful execution of the "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District" project. Our strong financial management practices, experienced team, and commitment to transparency and sustainability further reinforce our ability to deliver impactful results.

Expertise and Experience:

Our organization specializes in program and project management, WASH initiatives, infrastructure development, and capacity-building efforts. We have successfully executed multi-sectoral development projects in Afghanistan, working alongside international donors, government agencies, and community organizations. Our expertise includes:

- Project Planning & Execution: Comprehensive experience in designing and implementing WASH infrastructure projects.

- Community Engagement & Capacity Building: Strong focus on community participation, ensuring project sustainability.

- Monitoring & Evaluation (M&E): Robust impact assessment frameworks to measure success and make data-driven improvements.

- Sustainability & Policy Integration: Aligning projects with national and international development frameworks such as UNICEF’s WASH priorities and the Sustainable Development Goals (SDGs).

Key Personnel:

Our team comprises highly qualified professionals with expertise in engineering, WASH management, financial administration, and community development.

| Name | Position | Expertise |
| --- | --- | --- |
| Abdul Rahman Sadiqi | Program Director | Project Management, WASH Implementation |
| Abdul Habib Aulfat | Project Manager | Civil Engineering, Contract Management, PMP |
| [Key Engineer Name] | WASH Technical Expert | Water and Sanitation Infrastructure Development |
| [Trainer Name] | Community Trainer | Hygiene Promotion & Behavioral Change |
| [Finance Officer Name] | Finance & Compliance Lead | Budgeting, Donor Compliance, Financial Audits |

Our team’s deep technical expertise ensures that all components of the project—from design to execution—are managed effectively and align with best practices in WASH service delivery.

Resources and Infrastructure:

PMIC is well-equipped with the necessary resources and logistical capacity to successfully implement this project:

- Operational Facilities: Offices in Kabul and key provinces, providing logistical support for fieldwork.

- Project Management Systems: Use of advanced monitoring and evaluation tools for tracking project progress and impact.

- Field Teams & Mobile Units: Rapid response teams equipped with vehicles and necessary tools for project implementation.

- Training & Capacity-Building Centers: Facilities dedicated to training local stakeholders, school staff, and community WASH committees.

- Digital and Data Management Tools: Advanced software for financial tracking, reporting, and stakeholder engagement.

Past Achievements:

PMIC have successfully executed numerous developments, infrastructure, and WASH projects in Afghanistan. Some of our key accomplishments include:

| Project Name | Donor/Partner | Scope | Impact |
| --- | --- | --- | --- |
| Rural WASH Initiative – Takhar Province | UNICEF | Construction of water supply systems & latrines | Benefited 15,000+ individuals |
| Community Hygiene Education Program | Aga Khan Foundation | Hygiene awareness campaigns in schools | Reduced waterborne diseases by 30% |
| School Sanitation Improvement Project | ADB | Installation of school WASH facilities | Benefited 6,000+ students |
| Infrastructure Rehabilitation for Health Clinics | UNDP | Upgraded sanitation & water access in clinics | Served 10,000+ healthcare facility users |

These successful past projects demonstrate our capability to execute high-impact WASH interventions while ensuring sustainability and community participation.

Financial Management and Accountability:

PMIC follows international best practices in financial management, ensuring compliance with donor requirements. Our financial accountability mechanisms include:

- Transparent Financial Reporting: Regular financial audits conducted by independent certified firms.

- Budgetary Control Systems: Use of PMBOK-aligned financial tracking tools for budget oversight.

- Donor Compliance & Reporting: Strict adherence to UNICEF financial guidelines, ensuring proper fund utilization.

- Fraud Prevention & Risk Management: Comprehensive internal control mechanisms to prevent mismanagement.

Our commitment to transparency and accountability ensures that all funds are used efficiently and effectively to maximize project impact.

Partnerships and Collaborations:

PMIC has established strong partnerships with key stakeholders, including:

- UNICEF & UN Agencies – Collaboration in WASH, education, and health initiatives.

- Government of Afghanistan – Working with local municipalities and ministries for policy alignment and sustainability.

- Local NGOs & Community-Based Organizations (CBOs) – Partnering with grassroots organizations to ensure community involvement.

- International Donors (ADB, UNDP, Aga Khan Foundation) – Implementing large-scale infrastructure and development projects.

# Work Plan:

| Task | Start Date | Duration (Days) | End Date |
| --- | --- | --- | --- |
| Baseline Assessment | 2025-02-01 | 15 | 2025-02-16 |
| Community Engagement & Awareness | 2025-02-16 | 30 | 2025-03-18 |
| Design & Planning | 2025-03-01 | 20 | 2025-03-21 |
| Procurement of Materials | 2025-03-21 | 25 | 2025-04-15 |
| Infrastructure Development - Water Supply | 2025-04-15 | 45 | 2025-05-30 |
| Infrastructure Development - Sanitation Facilities | 2025-05-30 | 40 | 2025-07-09 |
| Capacity Building & Training | 2025-07-10 | 30 | 2025-08-09 |
| Monitoring & Evaluation | 2025-08-10 | 60 | 2025-10-09 |
| Final Reporting & Handover | 2025-10-10 | 15 | 2025-10-25 |

# Risk Assessment:

| Risk Description | Impact (1-10) | Likelihood (1-10) | Risk Score (Impact × Likelihood) | Mitigation Measures |
| --- | --- | --- | --- | --- |
| Delay in material procurement | 7 | 6 | 42/100 | Pre-plan procurement, establish backup suppliers, and ensure early ordering. |
| Extreme weather conditions (floods, droughts) | 8 | 7 | 56/100 | Schedule work around seasonal weather, use climate-resilient construction methods. |
| Security risks (conflict, instability) | 9 | 6 | 54/100 | Engage with local authorities, ensure security measures, and have contingency plans. |
| Community resistance to change | 6 | 5 | 30/100 | Conduct awareness campaigns and involve community leaders in decision-making. |
| Shortage of skilled labor | 7 | 6 | 42/100 | Train local workers, offer incentives, and coordinate with vocational training centers. |
| Financial constraints or budget overruns | 8 | 5 | 40/100 | Implement strict financial tracking, review budget regularly, and seek additional funding if needed. |
| Contamination of water sources | 9 | 4 | 36/100 | Conduct regular water testing, implement water purification measures, and educate the community on hygiene. |
| Political or regulatory changes | 7 | 5 | 35 | Maintain compliance with local policies, engage with government stakeholders proactively. |
| Delays in obtaining necessary permits | 6 | 6 | 36 | Start permit application early, maintain regular follow-ups with relevant authorities. |
| Equipment failure or lack of maintenance | 7 | 5 | 35 | Regular maintenance schedules, train local personnel for repairs, and keep backup equipment. |

Risk Scoring Interpretation

- Low Risk: Score 1-20 (Minimal impact, unlikely to occur)

- Medium Risk: Score 21-40 (Manageable but needs monitoring)

- High Risk: Score 41-60 (Critical risks requiring immediate mitigation)

# Budget Breakdown

| Budget Category | Description | Estimated Cost (USD) |
| --- | --- | --- |
| Project Planning & Assessment | Baseline assessment, community engagement surveys | $15,000 |
| Design & Engineering | Technical drawings, site surveys, approvals | $25,000 |
| Procurement of Materials | Pipes, sanitation materials, water tanks | $100,000 |
| Infrastructure Development | Construction of water supply & sanitation units | $250,000 |
| Labor Costs | Skilled & unskilled labor for construction | $80,000 |
| Capacity Building & Training | Training for local communities & WASH committees | $20,000 |
| Community Awareness Campaigns | IEC materials, workshops, behavior change programs | $10,000 |
| Monitoring & Evaluation (M&E) | Regular site inspections, performance assessments | $15,000 |
| Logistics & Transportation | Vehicles, fuel, site visits, supply delivery | $30,000 |
| Permits & Regulatory Compliance | Government approvals, environmental assessments | $10,000 |
| Contingency Fund (10%) Admin Cost | Unexpected costs, inflation adjustments | $55,000 |
| Total Estimated Budget | Overall project implementation cost | $610,000 |

Key Considerations:

- The budget includes a 10% contingency to address unforeseen expenses.

- Labor costs include fair wages for skilled and unskilled workers.

- Sustainability measures (like training) are included to ensure long-term impact.

- Community involvement costs are allocated for education and behavioral change.

# Sustainability Plan

Introduction

The long-term success of the Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District project depends on its ability to sustain benefits beyond the project implementation phase. Sustainability ensures that the clean water supply, improved sanitation facilities, and hygiene education programs continue to serve the community effectively without ongoing external intervention.

To achieve this, the sustainability plan incorporates technical, financial, institutional, environmental, and social components to maintain project outcomes. The strategies outlined below will ensure that the infrastructure and behavioral changes remain effective for years to come.

1. Institutional and Community Ownership

A key aspect of sustainability is ensuring local ownership of the project. This will be achieved through:

1.1 Formation of Community WASH Committees

- Establish Community Water, Sanitation, and Hygiene Committees (WASH Committees) that include local representatives, religious leaders, school authorities, and women.

- These committees will be responsible for overseeing the maintenance, management, and governance of water and sanitation facilities.

- Members will undergo training in facility management, maintenance, and financial planning to ensure independent operation after project completion.

1.2 Collaboration with Local Government

- Engage the Baharak District local government to integrate WASH infrastructure into the regional development plans.

- Secure government support for periodic facility inspections and financial assistance for repairs.

- Advocate for WASH policy enforcement in schools and healthcare centers to ensure long-term sustainability.

1.3 Engaging Schools and Health Facilities

- Train school administrators and teachers on WASH management practices to instill a culture of hygiene among students.

- Encourage schools and health clinics to allocate part of their budget for water and sanitation infrastructure maintenance.

- Appoint WASH champions (students and teachers) to monitor hygiene behaviors and promote best practices.

2. Financial Sustainability

To ensure continuous functionality, a financial strategy will be implemented through:

2.1 Cost Recovery Mechanisms

- Introduce a small community-based fee system where households contribute a nominal monthly fee for water system maintenance.

- Set up a WASH fund managed by the community committee for emergency repairs, sourced from contributions, local government funding, and small business sponsorships.

2.2 Partnership with Local Businesses

- Collaborate with local businesses, NGOs, and microfinance institutions to support WASH infrastructure financing.

- Provide incentives for private sector involvement in maintaining water systems, such as public-private partnerships.

2.3 Grants and Subsidy Models

- Work with UNICEF, NGOs, and government agencies to secure periodic grants for large-scale repairs and infrastructure upgrades.

- Advocate for subsidies on water purification and sanitation products, making them more affordable to the community.

3. Technical Sustainability and Infrastructure Maintenance

Ensuring the long-term functionality of water and sanitation systems requires ongoing maintenance and technical expertise.

3.1 Training of Local Technicians

- Train local technicians in plumbing, water treatment, and sanitation infrastructure repair.

- Establish a local network of trained WASH professionals who can be called upon for maintenance needs.

3.2 Preventative Maintenance Plan

- Develop a scheduled maintenance plan for water pumps, wells, and sanitation facilities.

- Conduct monthly inspections to identify potential breakdowns before they escalate into major failures.

3.3 Use of Durable, Climate-Resilient Materials

- Construct water and sanitation facilities using high-quality, weather-resistant materials to withstand climate variations.

- Ensure water storage and distribution systems are built for long-term durability.

4. Environmental Sustainability

Maintaining a healthy and sustainable environment is crucial for the project’s longevity.

4.1 Protection of Water Sources

- Implement water conservation techniques such as rainwater harvesting.

- Educate the community on avoiding contamination of water sources by promoting proper waste disposal.

4.2 Wastewater and Sanitation Management

- Introduce eco-friendly sanitation technologies such as biodegradable toilets and soak pits.

- Establish a waste collection system to prevent the pollution of local water bodies.

4.3 Climate Adaptation Strategies

- Ensure water supply solutions are climate-resilient, particularly in regions prone to drought or seasonal flooding.

- Promote the use of drought-resistant crops in agriculture to reduce water consumption.

5. Social and Behavioral Sustainability

To sustain the project's impact, behavioral change must be permanent within the community.

5.1 Continuous Hygiene Education

- Ongoing hygiene education campaigns will be conducted in schools, healthcare centers, and community gatherings.

- Distribute hygiene promotion materials such as posters, brochures, and radio broadcasts.

5.2 Women and Youth Involvement

- Women and youth will be empowered as WASH leaders, ensuring they actively contribute to sustaining hygiene improvements.

- Schools will integrate WASH topics into their curriculum, making hygiene education a long-term learning component.

5.3 Cultural and Religious Integration

- Align hygiene and sanitation messages with cultural and religious values, ensuring community-wide acceptance.

- Work with local mosques and religious leaders to reinforce hygiene education through sermons and community discussions.

6. Monitoring, Evaluation, and Reporting

Continuous monitoring and evaluation (M&E) will ensure the project's long-term effectiveness.

6.1 Community-Led Monitoring

- Train WASH committees to track water usage, sanitation conditions, and hygiene behaviors.

- Use simple reporting tools (such as mobile apps or paper checklists) to document progress.

6.2 Government and Donor Reporting

- Submit quarterly and annual reports to donors, government agencies, and community leaders.

- Conduct impact assessments to measure disease reduction rates and improved access to WASH facilities.

6.3 Feedback and Adaptation

- Set up a complaint and suggestion system where community members can report WASH-related issues.

- Adapt strategies based on feedback to ensure continuous project improvement.

# MEAL Plan

1. Introduction

The Monitoring, Evaluation, Accountability, and Learning (MEAL) Plan is designed to track the implementation, measure the impact, ensure accountability, and capture lessons learned for continuous improvement of the "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District" project. The MEAL framework ensures that the project meets its objectives, aligns with donor expectations, and maximizes benefits for the targeted communities.

This MEAL plan is structured around four key components:

- Monitoring: Systematic tracking of project activities and outputs.

- Evaluation: Assessing project outcomes and impact.

- Accountability: Ensuring stakeholder involvement and responsiveness.

| Project Objective | Indicator | Data Source | Frequency of Collection |
| --- | --- | --- | --- |
| Provide clean water access to 3,500 households | # Of new water supply systems installed | Project progress reports | Monthly |
|  | % Increase in households with access to clean water | Household surveys | Quarterly |
| Improve sanitation in schools & healthcare centers | # of latrines and handwashing stations installed | Construction site reports | Monthly |
|  | % of schools and clinics with functional WASH facilities | School and health facility reports | Quarterly |
| Promote hygiene awareness | # of community hygiene sessions conducted | Training session records | Monthly |
|  | % of community members adopting improved hygiene practices | Household and school surveys | Bi-annually |
| Enhance sustainability through community engagement | # of community members trained in WASH management | Training session records | Quarterly |
|  | % of WASH committees actively managing facilities | Committee meeting reports | Annually |

- Learning: Documenting insights for future improvements.

2. Monitoring Plan

Monitoring involves regular data collection, progress tracking, and performance measurement against the project’s goals.

2.1 Key Monitoring Indicators

The table below outlines key performance indicators for project monitoring.

2.2 Monitoring Tools

- Household and school surveys to measure water access and sanitation usage.

- Site inspections and progress reports to track construction and maintenance.

- Community focus group discussions (FGDs) to assess public perception of WASH improvements.

- Real-time monitoring through mobile data collection tools (where feasible).

3. Evaluation Plan

Evaluation will assess the effectiveness, efficiency, impact, and sustainability of the project.

3.1 Evaluation Types

- Baseline Evaluation (Month 1-2):

  - Conduct initial community assessments to establish water and sanitation conditions.

  - Collect baseline data on waterborne disease prevalence, hygiene practices, and WASH access gaps.

- Mid-Term Evaluation (Month 6-7):

  - Measure progress against initial benchmarks.

  - Identify implementation challenges and corrective measures.

- Endline Evaluation (Month 12-13):

  - Assess overall impact in reducing disease prevalence and improving water and sanitation access.

  - Identify successes, gaps, and lessons learned for future scaling.

3.2 Key Evaluation Questions

- To what extent has the project improved access to clean water and sanitation?

- How effective were hygiene promotion activities in changing behaviors?

- What challenges were encountered, and how were they addressed?

- Are WASH committees and local stakeholders equipped to maintain the infrastructure?

- How sustainable are the implemented water and sanitation facilities?

3.3 Data Collection Methods

- Surveys and Key Informant Interviews (KIIs) with community members and local leaders.

- Pre- and post-intervention comparisons to evaluate improvements.

- Water quality testing to ensure safety standards are met.

- Case studies to document human impact stories.

4. Accountability Plan

Ensuring accountability involves engaging beneficiaries, donors, and stakeholders in decision-making.

4.1 Community Engagement Mechanisms

- Establish Community WASH Committees to oversee project implementation.

- Organize feedback meetings with beneficiaries to discuss concerns.

- Conduct door-to-door consultations to understand user experiences.

4.2 Complaints and Response Mechanism

To ensure transparency and responsiveness, the following feedback mechanisms will be established:

- Toll-free phone line / SMS platform for community concerns.

- Suggestion boxes placed in schools, health centers, and communal areas.

- Monthly community meetings where beneficiaries can share experiences and grievances.

- Formal grievance redress process with clear escalation steps.

4.3 Donor and Government Accountability

- Provide quarterly progress reports to UNICEF and other funding agencies.

- Conduct joint site visits with government officials to ensure compliance with local regulations.

- Maintain financial transparency through regular audits and budget tracking.

5. Learning and Adaptation Plan

A strong learning approach ensures that challenges and successes inform future programming.

5.1 Learning Questions

- What factors contributed to successful WASH adoption in schools and households?

- What were the biggest challenges in implementation, and how were they overcome?

- How can this project be replicated in other districts with similar challenges?

- What improvements can be made in community engagement strategies?

5.2 Learning Documentation

- Monthly reflection sessions for project staff to discuss lessons learned.

- Knowledge-sharing workshops with other NGOs and government agencies.

- Case study development highlighting impactful community stories.

- Quarterly learning briefs shared with donors and stakeholders.

5.3 Adaptive Management

- If infrastructure maintenance issues arise, increase training for local technicians.

- If hygiene behavior adoption is slow, modify awareness campaigns to be more interactive.

- If financial sustainability is at risk, explore additional revenue streams for WASH committees.

6. Roles and Responsibilities in MEAL Implementation

A clear role distribution ensures effective MEAL plan execution.

| Role | Responsibilities |
| --- | --- |
| Project Manager | Oversees overall MEAL implementation, ensures project goals are met. |
| MEAL Officer | Designs data collection tools, analyzes monitoring and evaluation data. |
| WASH Committees | Conducts community-led monitoring, reports facility conditions. |
| Field Staff & Trainers | Conducts surveys, FGDs, and hygiene education sessions. |
| Finance & Admin Team | Ensures budget tracking, financial reporting for accountability. |
| Government Partners | Provides oversight, integrates project outcomes into policy. |

# Supporting Documents

1. Legal and Organizational Documents

- Registration Certificate – Proof of the NGO’s legal status.

- Tax-Exempt Status – Documentation of nonprofit or charitable status (if applicable).

- Memorandum of Association/Articles of Incorporation – Legal governance framework.

2. Financial Documentation

- Audited Financial Statements – Evidence of financial transparency and accountability.

- Budget Breakdown – Detailed and itemized budget for the proposed project.

- Bank Account Details – Information for fund transfers (if required).

3. Organizational Capacity

- CVs of Key Personnel – Qualifications and expertise of project team members.

- Organizational Chart – Representation of the NGO’s structure and reporting lines.

- Past Project Reports – Documentation of similar completed projects.

4. Project-Specific Documentation

- Needs Assessment Report – Data supporting the necessity of the project.

- Project Work Plan (Gantt Chart) – Timeline and implementation schedule.

- Risk Assessment Plan – Identification of potential project risks and mitigation strategies.

- Sustainability Plan – Strategies for ensuring long-term impact.

5. Technical and Operational Documents

- Technical Drawings and Specifications – Infrastructure or equipment details (if applicable).

- Maps of Project Area – Geographic location and project site details.

- Memorandums of Understanding (MoUs) or Agreements – Any formal agreements with partners or stakeholders.

6. Stakeholder and Community Engagement

- Letters of Support – From local government, community leaders, or other stakeholders.

- Community Engagement Plan – Description of how the community will be involved in the project.

- Monitoring and Evaluation (M&E) Framework – Methods for tracking progress and impact.

7. Additional Documentation

- Photographs or Case Studies – Supporting visuals of project areas or past projects.

- Communication Plan – Strategy for disseminating project outcomes and updates.

- Procurement Plan – Outline of how materials and services will be sourced.

# Grant Proposal Submission Checklist

This checklist ensures that your grant proposal for the "Enhancing Water and Sanitation Facilities for Health and Hygiene in Baharak District" is complete, well-structured, and meets donor requirements.

1. Core Proposal Documents

✅ Cover Letter – Signed by an authorized representative
✅ Title Page – Includes project name, applicant organization, date, and contact details
✅ Table of Contents – Lists sections with page numbers
✅ Executive Summary – Concise project summary, objectives, impact, and funding request
✅ Statement of Need – Justification for the project, data-supported problem description
✅ Project Objectives – SMART objectives aligned with funder priorities
✅ Target Population & Beneficiaries – Detailed breakdown of direct and indirect beneficiaries
✅ Organizational Capacity – Demonstrates NGO expertise, key personnel, and infrastructure
✅ Work Plan (Gantt Chart) – Timeline with key activities and responsibilities
✅ Risk Assessment – Identifies potential risks, impact, likelihood, mitigation measures
✅ Budget & Financial Plan – Itemized budget with cost justifications
✅ Sustainability Plan – Ensures project continuity beyond funding period
✅ MEAL Plan – Monitoring, Evaluation, Accountability, and Learning framework

2. Legal & Organizational Documents

✅ NGO Registration Certificate – Proof of legal status
✅ Tax-Exempt Status – Documentation if applicable
✅ Memorandum of Association/Articles of Incorporation – Governance framework

3. Financial Documentation

✅ Audited Financial Statements – Ensures financial transparency
✅ Detailed Budget Breakdown – Itemized project costs
✅ Bank Account Details – For fund transfers (if required)

4. Organizational Capacity Documentation

✅ CVs of Key Personnel – Qualifications and expertise of the project team
✅ Organizational Chart – Shows reporting structure and key roles
✅ Past Project Reports – Demonstrates track record of similar completed projects

5. Project-Specific Supporting Documents

✅ Needs Assessment Report – Data supporting project necessity
✅ Project Work Plan (Gantt Chart) – Timeline and implementation schedule
✅ Risk Assessment Plan – Potential risks and mitigation strategies
✅ Sustainability Plan – Ensures long-term impact

6. Technical & Operational Documents

✅ Technical Drawings & Specifications – Infrastructure details (if applicable)
✅ Maps of Project Area – Geographic location and project site details
✅ MoUs or Agreements – Signed agreements with partners or stakeholders

7. Stakeholder & Community Engagement

✅ Letters of Support – From local government, community leaders, or partner organizations
✅ Community Engagement Plan – Outlines involvement of local stakeholders
✅ Monitoring & Evaluation (M&E) Framework – Defines performance tracking methods

8. Additional Documentation

✅ Photographs or Case Studies – Visuals of the project site or past initiatives
✅ Communication Plan – Strategy for sharing project progress and results
✅ Procurement Plan – Explanation of how materials and services will be sourced

Final Review Before Submission

✔ Ensure all documents are in the required format (PDF, Word, Excel, etc.)
✔ Check for typos, inconsistencies, and missing information
✔ Have a colleague or expert review the proposal for clarity and completeness
✔ Confirm all attachments are included in the submission package
✔ Submit before the deadline

✅ Proposal Ready for Submission!